## Sheet1
Material | Approximate Cost | Procurement Strategy
Large dustbin | 1200 | Amazon
Ultrasonic sensor (4) | 150*4 = 600 | Amazon
Arduino Mega | nil | Lab
Motors for hands and base (7) | 150*7= 1050 | Ebay
Large box for grabbing | nil | will use an old box kept at home
Rods for arms (Curtain rods) | nil | will use old ones kept at home
Big Motor for piston | 1000 | Amazon
GSM Module | nil | Lab
Breadboard, connecting wires etc | nil | Lab
Materials for base and piston | 400 | Different Sources
Approximate Total Cost | 4250
Risk Identification | Risk Response | Risk Probability
A person might drop his/her valuables near the dustbin, which directly go inside the bin. | It is better that the valuables be hidden inside the bin than remaining on the floor where someone can just pick them up. The valuables can be recovered easily if they are secured in the bin through services like findmyphone for phones etc. | Medium
Worker may be absent at time of the bin is completely filled. | Initial messages will be sent to the centers when 50%,70% and 90% of the bin is filled. | Medium
There may be some malfunctioning in the parts of the system. | Checking the equipment carefully before buying so that we face no issues in the future. | Medium
The software and hardware platforms we are using may become obsolute. | Keeping a basic model of the entire project which can be applied to updated versions. | Low
There can be delays during implementation of a particular step in the Work Breakdown Structure. | The completion date has been set up 2 weeks before the deadline. | High
The base might not be able to hold the burden of the bin and its content | Stronger wheels and more powerful motors can be used. | Medium
| Big Motor for piston | 1000
| GSM Module | nil
| Breadboard, connecting wires etc | nil
| Materials for base and piston | 400
| Approximate Total Cost | 4250