## Sheet1
WBS |  | 3 weeks | - | 1.5 week | .5 week | 1 week
Create Rotating Base | Set up sensors | Set up arms | Calibrate arms to work with different objects | Set up Piston | Set up message sending service | Testing and Troubleshooting
Create basic structure of base with provision for sensors | Buy dustbin and sensors | Buy box(for grabbing), rods for arms and motors | Check arms for different objects ranging from paper balls to bottles | Cut metal/wood pieces in the required shapes with a hole in the base of the piston for the sensor | Add GSM module | Combine working of arms, base and piston.
Set up motors and wheels | Add sensors to base | Cut box | Change code as appropriate to accomodate different objects |  | Set up sending of messages according to sensor readings | Run various tests on the bin and fix any errors
Write code to rotate the base | Write code to rotate the base based on sensor output | Attach arms,motors and box
Get Arduino and control base using the Arduino |  | Add arms to dustbin
Set up arms to work with sensors
Set up box to pick things up